## Project Title: An interactive, on line numeracy resource for pre-registration student nurses and midwives.

## Project Leader: Sarah Green, Director of Educational Partnerships

Department/School: Faculty of Health and Life Sciences

## Institution: University of the West of England

## Abstract:

Nursing and midwifery education is facing significant change with it moving to an all graduate profession by 2013 (DH 2008; NMC 2008). The shifting policy context demands a highly skilled workforce that is able to manage increasing complexity, long term conditions, technologies and medicine management. Numeracy is part of the Nursing and Midwifery Council’s professional standards and as such all students have to successfully pass a first and final year assessment in their three year programmes as it directly impacts on patient safety. In addition, our partner organisations report numeracy is an under developed skill in the qualified profession. In collaboration with mathematics colleagues this project has developed an on line numeracy resource with two main components. One is the use of an on line assessment system DEWIS that has been adapted to enable students to self-assess their level of numeracy. The second is an on-line decision making tree that is populated with patient case studies and applied numeracy skills. This twofold approach will provide a flexible resource with the potential for a far reaching impact across the South West region and all gateways to higher education.

List of Outputs:

- An adapted on line DEWIS assessment system for nursing and midwifery students. Collaboratively mathematical and nursing and midwifery academics have developed and implemented numeracy questions that are appropriate for the student body. The difference of this on line assessment system to others is that it enables an individualised system allowing the student to self-evaluate, identify and rectify their own knowledge level. - An on-line decision making tree that is populated with patient case studies and applied numeracy skills. If students make errors in their calculations they are able to see the impact of their decision, for example, a patient collapsing or cardiac arrest. It is still hoped this will evolve into an avatar resource if increased funding becomes available to resource this work effectively - A new working relationship between the Nursing Department and the Mathematics Department at the University.

Project Highlights:

## Collaboration with colleagues at UWE in mathematics - Raising the profile of numeracy skills for nursing and midwifery students - Utilising technology for a skills based teaching

Background and Rationale:

## Prior to undertaking this work nursing and midwifery numeracy skills were primarily assessed through workbooks, clinical assessments and an on-line numeracy exam. These tools ensured the professional NMC standards for numeracy were upheld in the undergraduate programmes (NMC, 2010). To some extent these methods of assessment are able to assess, and test, student ability although, it is fair to say that how these competencies are applied, and equate with safety in the clinical practice is a matter of debate. Indeed, from discussion with our clinical stakeholder’s numeracy skills, as applied through medication administration, is an area of anxiety for the newly registered professional and remains an area where poor practice is frequently reported. ## There are an increasing number of on line resources available for nursing and midwifery numeracy, such as ‘maths lab’ from Pierson publishing, however, are not embedded into pre-registration programmes and students can opt out of using them. This project has also illustrated that in order to enhance numeracy skills there must be ongoing collaboration between HEIs and clinical areas. In order for numeracy skills undertaken as theoretical and virtual study to be applied and understood in clinical practice, students must be aware of the lived world experiences of medicine administration. Students must gain an awareness, therefore of the distractions, demands and pressures experienced in practice environments where professionals have to undertake calculations for safe medicine administration. ## In this way this project set out to establish an environment that would not only assist with numeracy skills but help students clearly understand their own aptitude and ability when undertaking numeracy assessments. This may sound an obvious statement, but reports from our organisation suggest many students take numeracy tests which they either pass or fail; however, very few develop the insight into how they as an individual tackle and develop numeracy skills. This is essential for autonomous decision making integral to the role of the nurse and midwife. In this way, it was anticipated that this assessment system would immediately help with numeracy development but in addition help develop leadership and concise decision making increasingly necessary for the complex future facing nursing and midwifery.

## Implementation:

Initially the project focused on selecting the appropriate individuals to be involved in this work. The key project team consisted of Associate Heads of Department for nursing and midwifery, Director of Educational Partnerships and senior mathematical lectures. Prior to this project there were no links between the mathematical Department and nursing and midwifery. This seemed an obvious gap as both offered unique application and understanding. The mathematicians were able to provide significant expertise surrounding numeracy, while the nursing and midwifery staff provided the context for this work. The context setting enabled mathematical staff to understand the clinical environment and specific demands facing nursing and midwifery. Consequently, it became increasingly apparent that a combined approach offered an expertise to guide the work that was previously unavailable and core to the success of the project. Pre-arranged meetings between the project team enabled understanding of the different cultures and professions to be gained. Without these opportunities it would have been difficult to focus on shared objectives that were the focus of the work. Furthermore, these opportunities to share, and discuss, provided a much needed space for HEI staff to explore opportunities and work streams that were not always directly related to this project. During the early stages of the project the group met more regularly, while as work became more tangible, less direct face to face meetings were required and more on line communication occurred. The importance of this network and professional space must not be underestimated and has been a significant gain to the work. This has been recognised at an individual and institutional level. During the progress of this project a much wider, than initially anticipated, collaboration with academic staff was required. In part this may have been due to the internal turbulence that existed during the course of this project. Shortly after the start of this work the University started to undertake change management strategies that resulted in restructuring across the Faculty and Nursing and Midwifery Department. Many of us working in the project team were directly affected and had to apply for new or existing roles. Many of us have now found ourselves in different roles to that which we were in at the beginning of this project. This has undoubtedly been an area of weakness for this project as many of us that had roles directly linked with pre-registration programmes were re-structured into new roles that no longer had direct interface with these programmes. The ongoing commitment of the project team has to some extent helped overcome these challenges and highlights the importance of embedding a project within the business of the Faculty rather than professional posts. To help overcome this unpredicted risk, staff still directly involved with teaching and management of the pre-registration programmes were employed to help support the work. A key area of support came from academic staff responsible for medical prescribing programmes in the Nursing and Midwifery Department. Although, these are post registration programmes, the expertise of medication management was invaluable and provided some stability to the changing profile of the project team. Ongoing collaboration also occurred with stakeholders. By and large, this took place through Departmental meetings that had large stakeholder representation. These meetings enabled exploration, with clinical practice, on the skills that nursing and midwifery students need to be equipped and empowered to do in the clinical environment. Once again, as with the internal turbulence of the HEI, external pressure facing health and social care organisations did influence this activity. During this time period many of the University partners have, and continue to be, undergoing significant change such as the shift from acute care to community setting and many PCTs becoming social enterprises. In hindsight it may have been useful to have established a senior project board to oversee numeracy skills development that would have continued this work into the future. Having said that, current Department business planning is looking to review many of our structures and look to ways to further consolidate our collaboration with our health and social care partners. This project will help inform this work. As stated in the project objectives, the on-line DEWIS system has been successfully adapted for the numeracy assessment of nursing and midwifery students. In order for this to have occurred ongoing collaboration was necessary between the Nursing and Midwifery Department and those in mathematics. An unexpected challenge was the use of the DEWIS software being compatible with the Department’s and external IT systems. This was overcome by early involvement of senior IT colleagues so that the DEWIS system ensuring compatibility. The end result has been the development of software that has applied questions for nursing and midwifery students which has the ability to demonstrate how questions should be ‘worked out’ according to the student undertaking the test. This has offered a different dimension to assessments already in existence and will enable students question, reflect and analyse skills in relation to numeracy. The virtual patient is already in development at UWE and part of this work has been investigating medicine management. In the original proposal it was planned that this work would be further developed so that once having undertaken the on line assessment students could then apply numeracy knowledge in a virtual clinical environment of medicine management. This would create the skills of numeracy as highly relevant and visually illustrate the impact of these skills on patient safety. This was discussed with the technology enhanced learning team with identified resources. These resources were eroded during the course of the project due to the Faculty demands facing on line learning development. As a result, the team discussed how we could realistically; with the financial constraints, develop a patient on-line resource. The end product has become an on-line decision making tree that is populated with patient case studies and applied numeracy skills. If students make errors in their calculations they are able to see the impact of their decision, for example, a patient collapsing or cardiac arrest. It is still hoped this will evolve into an avatar resource however; increased funding is required to effectively resource this work. In terms of dissemination, the original proposal included the marketing of the resources developed for a wider audience of learner profiles. UWE has a wide range of partnerships that enables a full spectrum of learning gateways from levels 4, 5 and 6. For example, partnerships arrangements with FE organisations that enable direct entry into our nursing programmes from non-traditional backgrounds. Therefore, the resource could have a far reaching role to play beyond that of solely pre-registered nurses and midwives. It could be used to provide a resource for qualified nurses and midwives and in our widening participation strategies. In addition, the proposal included a plan to disseminate the findings from the project through academic conference presentations and academic publications. These plans for dissemination within the timescale of the project have been affected by the restructuring of the University described above. However, the Project Leader’s new role as Director of Educational Partnerships role will provide opportunities to disseminate the findings widely and translate into further business and influence. Discussions are already taking place for its use with foundation degrees. For example, the University supports a number of widening participation agendas with many foundation degrees feeding into our pre-registration programmes. The use of this resource would help support these students and help the transition into a HEI organization with different expectations and cultures. The project team did complete the evaluation stage later than initially intended due to uncontrollable challenges facing the internal structures of the university. Therefore, data analysis has just been completed and the project team needs to meet and discuss where we progress from here. Part of this will review any necessary modifications or students focus as the ultimate aim of this project is to enhance safety and student experience. The team is also in the progress of identifying appropriate journals and conferences for dissemination of the work. This will look to a diverse audience range from service users, stakeholders and academics.

Evaluation:

Seventeen test attempts were made on the Dewis system using the questions developed as part of the project. Of these attempts 13 students took part in the evaluation of the project. The test scores are summarised below. Student; Score; Max Possible; % age. 1; 6; 15; 40%. 2; 10; 15; 67%. 3; 11; 15; 73%. 4; 14; 15; 93%. 5; 9; 15; 60%. 6; 4; 15; 27%. 7; 8; 15; 53%. 8; 7; 15; 47%. 9; 10; 15; 67%. 10; 9; 15; 60%. 11; 13; 15; 87%. 12; 10; 15; 67%. 13; 8; 15; 53%. 14; 13; 15; 87%. 15; 7; 15; 47%. 16; 11; 15; 73%. 17; 14; 15; 93%. A number of students repeated the test and improved their overall scores which would indicate that the DEWIs system does allow students to develop their skills by exploring where they had made mistakes on the questions. Students were asked to evaluate the test using the following questions. Question 1 Do you feel confident about your numeracy skills? Yes ¦ No Question 2 Did you complete all the questions in the time allowed? Yes ¦ No Question 3 Did you need to use any support materials (e.g. books, calculators or web-based material) to complete the questions? Yes ¦ No Question 4 What was your final test score? Question 5 When answering questions incorrectly were you able to determine where you made mistakes? Yes ¦ No Question 6 Did this test help you understand numeracy processes? Yes ¦ No Question 7 Was the test easy to access? Yes ¦ No Question 8 Was the test easy to use? Yes ¦ No Question 9 Have you any suggestions as to how this e-assessment could be improved? Students were asked to fill in the questionnaire and responses are below: STUDENT: 02977610 CONFIDENT: no COMPLETE: yes SUPPORT: yes FINAL SCORE: 65 CAN DETERMINE MISTAKES: yes HELPS TO UNDERSTAND: yes EASY TO ACCESS: yes EASY TO USE: yes STUDENT: 02977610 CONFIDENT: no COMPLETE: yes SUPPORT: yes FINAL SCORE: 96 CAN DETERMINE MISTAKES: yes HELPS TO UNDERSTAND: yes EASY TO ACCESS: yes EASY TO USE: yes COMMENTS: Enter your comments here.... STUDENT: 11019270 CONFIDENT: yes COMPLETE: not Ans SUPPORT: yes FINAL SCORE: 9//15 CAN DETERMINE MISTAKES: yes HELPS TO UNDERSTAND: yes EASY TO ACCESS: yes EASY TO USE: yes COMMENTS: Enter your comments here.... it's good STUDENT: 09021722 CONFIDENT: no COMPLETE: yes SUPPORT: yes FINAL SCORE: 65 CAN DETERMINE MISTAKES: yes HELPS TO UNDERSTAND: yes EASY TO ACCESS: yes EASY TO USE: yes The majority of responses indicated that students were not confident about their numeracy skills but were confident that the test supported their development.

Discussion, Learning and Impact:

Due to time constraints and organisational structural changes the development of the project did not progress as far as expected, but has provided valuable learning: - We can pull together seemingly different professions to work for a common cause - Partnerships between Nursing and Mathematics have been developed – this will continue to enhance the student experience of the system developed - The Nursing team have focused on numeracy in a way not previously thought about – engaging with students to understand their needs - There is a will to develop numeracy in health and bring together the whole faculty. - The approach was successful as it drew upon people’s strengths: networking; student engagement; nursing focused; technology enhanced learning was embedded, and a pilot was achieved. What was effective or beneficial about the work with particular attention given to impact on the target audience: - The most beneficial aspect about this project was that students engaged with the system and did so repeatedly - Students have also noticed the University wants to support them to enhance the skills they tell us they are least confident in, namely numeracy Where your work has had an impact at an: - individual level – engagement in a project despite the time constraints has provided a unique insight into technology and how it can be used for the benefit of people who would normally engage with it - department level – drew people from all backgrounds together, including a pharmacist and IT to support the project - faculty level – the faculty’s profile has been raised with respect to gaining monies and developing a project that will be beneficial for health - institutional level – across faculty working which was limited over eighteen months ago What would you do differently if you were to undertake the activity again (and why), and what advice would you give to others wishing to undertake similar work? - overestimate the time required to engage with the project – coordinating diaries in the first instance and ensuring things go well requires investment of time - during the pilot project have further engagement with students to keep up the momentum – there was an awareness of this but also not wanting to influence student evaluation - ensure those staff engaged at the start identify barriers to what could prohibit engagement throughout Enablers: - Motivation - Technology - Expertise in mathematics and nursing Barriers: - Time constraints Key Learning - More interactive systems needs to be developed to engage all students - The virtual patient scenarios require embedding into the system to ensure the recreation of a live environment - Staff development as outlined above - Student development through engaging with the new material - Building numeracy into the taught curriculum in the first year, and even on admission

Further Development and Sustainability

Will the activity continue in the future? (a) Yes (in its current form) (b) Yes (in a modified form) (c) No/Unsure If you answered (a), how has this sustainability been achieved and in particular how have you enabled the activity to continue without HE STEM funding or direct support? If you answered (b), how will the continuing activity differ, for example, in its structure or delivery? How will the activity be sustainable and continue as a result of this modification? The resource will be utilised for students, however, an unforeseen major curriculum review of undergraduate programs will impact on the use of this resource. The resource will need to be modified to ensure it complements new learning technologies that will become part of this review. If you answered (c), what has prevented the activity from becoming sustainable? What will now happen to the activity? If you answered ‘unsure’, upon what does sustainability depend?

In relation to the approaches to sustainability outlined below, we are very interested in activities and commitments which have occurred within the timescale of the project. However, we recognise that some approaches may still be in the development phase at the official project end date and it would also be valuable to include these examples in the template.

| Approaches to Sustainability | Examples | In relation to your project |
| --- | --- | --- |
| Continuance (finding alternative sources of funding) | ## Commitment from HEI and practice institutions to provide continued funding - Network/ communities likely to be sustained through inclusion in future funding bids | ## The future of this work is being considered as part of the curriculum review facing nursing and midwifery. Internal networks with mathematical colleagues. |
| Embedding (within institutional activity) | - Identification of institutional strategies that the project has informed - Uptake which has taken place, or is likely to take place, within own/other HEIs - Influencing of organisations external to HE Sector which has occurred through partnership working |  |
| Mainstreaming (changes in working practices) | - Staff development which is planned or has taken place as a result of your project - Curriculum enhancement that has occurred or is likely to take place as a result of your project - Influence of senior managers that has arisen as a result of the project | ## Staff development as outlined in the Discussion, Learning and Impact section Numeracy skills for nursing and midwifery students recognised at strategic level in the University |
| Legacy (passing on important elements of the project) | - Networks/communities likely to be continued - Dissemination of project outputs - Evidence of impact of activities - Creative Learning Journey material made available via the SW Spoke Creative STEM website where relevant. | Karen Henderson and Rhys Gwynllyw contributed to Open Source E Assessment Workshop at Manhester Met on Wednesday 14th March 2012 |

## References:

Department of Health, 2000. An organisation with a memory, report of an Expert Group on Learning from Adverse Events in the NHS Stationary Office London. DEWIS online at http://www.cems.uwe.ac.uk/caa/welcome/ (last accessed 25 Nov 2010) Nursing & Midwifery Council (2010) Standards for pre-registration nursing education, London. Online at http://www.nmc-uk.org/Publications-/ (last accessed 24/11/10).

Quotes:

Involvement in the HE STEM project has enabled numeracy skills for nursing and midwifery students to be recognised at a strategic University and clinical partner wide level. This has been largely due to the networks that have formed between academic colleagues, students and stakeholders during the course of the work. These networks cannot be overestimated as they provide the relationships on which, against an increasingly fragmented backdrop, the success to service improvement and collaboration are based upon. Sarah Green , Director of Educational Partnerships, UWE