Practice Transfer Adopter Evaluation

‘Developing a Community of Practice for STEM Outreach Practitioners’

Achievements to Date

Project time scale:

| February 2012 | Project Briefing Birmingham |
| --- | --- |
| March | Initial discussions and securing of internal and external staff time |
| March | Planning reviews and development timeline |
| April | Peer-Reviews begin |
| April | Peer-Reviews continue |
| May | Visit to partner institution – University of Hertfordshire/St Aidan’s |
| June | Exeter Dissemination Event |
| July | Project End Evaluation & e-launch |
| October 2012 | Official PTA Booklet Launch at the 2012 Bradford Science Festival |

The above table lists the project time line in relations to the PTA here at the University of Bradford and below is a summary of the achievements of the PTA at the University of Bradford and its partners.

- Four Peer Reviews of Outreach Activity

  - Faraday Challenge

  - Shirley Manor Primary

  - St Aidan’s STEM Careers event

  - NG Bailey Robot Challenge

- Two PTA Visits to acquire new working practices

  - University of Hertfordshire

  - St Aidan’s CE High School

- New Partnerships

- STEM at Bradford Blog

Project Outputs

- The University of Bradford PTA Booklet

Summary of contents of the booklet…

  - Peer Reviews

  - Summary of Communities of Practice

  - Bradford STEM Activities

  - STEM Lab

  - Dissemination Event

- New Partnerships

  - June Visit to the Faraday Challenge

    - Colleagues from the University of Hertfordshire

    - Colleagues from the Royal institute of Engineering

  - Project dissemination events at the University of Exeter and University of Birmingham

- New programme development and delivery

The opportunities afforded through this adopter have enabled key outreach staff to widen their own practice and networks. This is invaluable as currently STEM outreach is managed across the university on an individual basis – peer reviewing activity at partner institutions has been a mechanism for opening up dialogue across the university between STEM practitioners.

As a result of the Faraday Challenge observation, the University is now considering how such an event may benefit Bradford communities and is looking at staging a similar event. Partnering with ST Aidan’s High School and being part of the STEM Careers evening has also opened up new avenues for the University in that we are working together to create a model of STEM Careers events which could be trialled at inner city Bradford schools. Supporting Primary schools to think about going for the PSQM award will benefit the district enormously as the adopter showed us that there are no other Bradford schools involved. This is something the new STEM Centre could facilitate and we are now actively pursuing this as an option of support in our programme.

Issues

There have been two keys that have presented themselves through the course of the project. As to the staff structure and the current challenges in the outreach area, securing staff time within the university and staff time in partner institutions has proven challenging.

Due to the nature of the short timescale through to the end of the HE STEM it has been challenging to build in sustainability.

Dissemination

PTA e-launch – July 2012

The project is to be initially launched with its partners and schools as an e-bulletin to ensure teacher engagement.

Bradford Science Festival – October 2012

The launch of a hard copy of the completed PTA brochure is due at the Bradford Science Festival in October 2012. This will enable time for the booklet to be further developed as a tool to support engagement between the university and schools in the context of our new STEM Centre.

Evaluation

The visits to meet PTA colleagues at the meetings facilitated by the Exeter team proved the most effective in building strong relationships with new stakeholders and STEM outreach organisations. The opportunity the programme allowed to visit an activity at another partner institution proved invaluable to encouraging development and adopting of good models of working practice. The PTA activity will be evaluated as part of the wider Building STEM at Bradford Programme which has a strong formative evaluation strategy. A dedicated Evaluation Manager is capturing the journey of the project and all associated activity – in this way the contribution of the PTA to the wider institutional objectives will be drawn out.

Sustainability

The PTA has led to the production of a much-needed STEM outreach brochure which, in the recent years, has been identified as an area of development. This project has allowed staff and financial resource to be assigned for the development and production of a brochure.

The peer-reviews provide the core content to the brochure that also advertises all outreach provision at the university for its key stakeholders and the school, colleges and academies. In the current access and widening participation environment (where previously, key central hubs disseminated information and updates from HEIs, i.e. Aimhigher), the PTA booklet / brochure is proving a useful gateway to disseminate information to partners as a hard copy brochure and electronically.

The university has found this tool useful as it fulfils a gap in STEM outreach provision, with the development of the STEM lab at Bradford, which is due to open next year. There is a commitment for this brochure to be a key promotional tool of the STEM lab facility and the programmes it will present to its local STEM community.

Support/Feedback to Exeter

The PTA has provided a great opportunity to develop and produce a new and innovative form of peer review evaluation and platform for promotion of STEM Outreach at Bradford.

The support provided by the team at Exeter has proved essential and integral to adding value to the project and also facilitating the cross-institutional collaboration of the PTA. We would be very keen to continue these partnerships beyond the HE STEM programme and hope there is reciprocal support through the other partner institutions.

.

Janet Smith-Harrison

Mutty Dad

University of Bradford

July 2012